Valley County Airport Commission

Tuesday March 8, 2022

Wokal Field Airport Terminal Building

89 Airport Road

Glasgow, MT

PRESENT: Joe Reyling, Russell Leader, Darrell Morehouse, Kristie Brabeck, Jayson Nelson, Manager Lucas Locke

ABSENT: Secretary Darcia Schindler

OTHERS:

The meeting was called to order at 6:10 p.m. by Chairman Jayson Nelson, Chairman Nelson called for public comment.

February 8, 2021, meeting was reviewed.

A motion was made by Russell Leader and seconded by Kristie Brabeck to approve the minutes with correction to the cash balance. Motion carried.

February Claims

| Arch’s Tire | Repairs | 133.00 |
| --- | --- | --- |
| Aviation Planning Group | Pavement Maintenance | 4,100.00 |
| City of Glasgow | Utilities | 34.82 |
| City Service Valcon | Jet Fuel | 34,960.88 |
| Ezzie’s | Airport Fuel | 152.90 |
| Fall Line | Repairs | 3,039.31 |
| HI Line Ford | Repairs | 375.04 |
| Jeremy Stringer | Refund | 400.00 |
| Markle’s Inc., | Supplies | 260.96 |
| Markle’s Inc | Supplies | 44.98 |
| Markle’s Inc. | Supplies | 56.53 |
| Markle’s Inc. | Supplies | 31.99 |
| Markle’s Inc. | Supplies | 23.97 |
| MDU | Utilities | 1,030.50 |
| Northern Montana Textile Services | Mats | 32.96 |
| NorthWestern Energy | Utilities | 1,992.15 |
| NorVal Electric | Utilities | 32.10 |
| O’Reilly Auto Parts | Supplies | 31.99 |
| O’Reilly Auto Parts | Supplies | 58.54 |
| Visa ~ Airport Card | Supplies | 693.22 |

The following claims were presented for review and approval.

A motion was made by Darrell Morehouse and seconded by Joe Reyling to approve the claims. Motion carried.

FINANCE REPORT:

Cash Balance on February 1, 2022,	            $232,634.79

Income		                	    	    51,027.66

Expenses 			 	 	   -66,985.01

Cash Balance on February 28, 2022,   	$216,677.44

FUEL SALES REPORT

February 	Airport Operations:	343

| Jet Inventory: |  | 6,500 |  |
| --- | --- | --- | --- |
| Purchased 7,000 gal |  | 2/12/2022 | $3.50 |
| Our Current Price: |  |  | $4.90 |
| Current wholesale: |  |  | $4.04 |
| Our Markup: |  |  | $1.40 |
| 100LL Inventory: |  | 6,000 |  |
| Purchased 9,800 gal |  | 1/24/2022 | $4.46 |
| Our Current Price: |  |  | $5.50 |
| Current Wholesale: |  |  | $5.49 |
| Our Markup: |  |  | $1.04 |

AIRPORT MANAGER’S REPORT

F-150:	Repaired at Hi-Line Ford for leaking power steering hose.

Plow truck:	Ordered one set of plow edges for the trucks. Price increase by 32% from last year.

Job Opening:	Job has been posted again.

Airport Terminal Program:	The FAA has announced a funding opportunity for new or updated airport terminal buildings. Over the next five years there is $5 billion available.

CAPE AIR REPORT

No Report Received

New Cape Air Schedule:	GGW-BIL Depart 0746 - Arrive 0900

Effective March 21

BIL-GGW Depart 1003 – Arrive1120

GGW-BIL Depart 1152 – Arrive 1306

BIL-GGW Depart 1821 – Arrive 1938

NEW BUSINESS

DOWL Report

Projects Info

Master Plan / Aerial Survey / ALP

• Inventory / Facility Requirements Chapters in Draft

• Forecast Chapter requires FAA approval. Forecast methodology approved by FAA and underway

Pavement Maintenance - Design

• 90% & 100% draft design approved by FAA.

• Bid announcement printed in paper tomorrow.

• Bid Package will be uploaded to AEPlans tonight

• Bids will be due back March 28th, at 10:00. Bid opening will immediately follow

• FAA did approve txy C as eligible if timeline of current CIP is approximately right.

• Stopways were deemed ineligible by FA, but were included as additive alternate in bid so that the Board can decide if they want to complete them without FAA assistance

REIL Replacement Project – Design & Construction

• REIL project completed. FAA closeout of the project is tied to runway pavement maintenance design project (same FAA grant). RFR 004 was submitted and approved just today. Next RFR will be for final amount and project closeout.

Pavement Maintenance - Construction

• It is anticipated that construction will be completed late summer or very early fall

• FAA grant needs to be submitted for contract award amount and CA / Bid services

  - • CA scope and fee estimate was submitted for IFE, and is within 10% o FAA airspace / project coordination form, CSPP, IFE, RON, bid package are part of the CA

  - • DOWL will prepare Record of Negotiation for GGW submittal to FAA within a week

  - • GGW received $50,400 for appx 90% of est sponsor share of project costs by MDT in January

Other Items

Big Timber NPE transfer – As per previous GGW Board discussion, repayment will NOT be made this fiscal year, or at least DOWL recommends waiting until bids are let in February to determine what available NPEs are required for project prior to committing any transfer to Big Timber

FAA Covid / Infrastructure Relief Grants

• CARES Act / CRRSA Act / ARPA Act – Lucas applied for and received grants for each of the FAA CoVid relief grants. Lucas handled all aspects of these grants and has further information

• BIL Funding – GGW was recently awarded funds totaling $159,000, each year, for a 5-year period, starting this fiscal year (FY-22) as part of the congressional Bipartisan Infrastructure Law (BIL). Funds will be administered by FAA grant, similar to FAA NPE funds, at 90% match (some exceptions for 95%). Airport BIL project eligibility follows FAA Passenger Facility Charge (PFC) rules, which are similar to NPE rules, but have a bit more flexibility. BIL funds cannot be transferred between airports, like NPE funds. Like NPE funds, airports may accrue funds for up to 3 years, and obligate in the 4th, (Please see attached GGW CIP/BIL plan). BIL funds can be used in conjunction with NPE funds for projects, but, they require a completely separate grant application, grant administration and RFR process (doubling the grant admin work for projects). BIL funds cannot be used for a sponsor’s 10% match funding for NPEs (and vice versa). FAA requires a new CIP submitted by March 15th, if using BIL funds this fiscal year (GGW is not currently planning that).

FAA annual DBE report

• DOWL (Megan Zollars) is waiting for FAA (Sonja Cruz) approval to submit annual DBE reporting

Draft Capital Improvement Plan (CIP) & Discussion

• Attached you will find a DRAFT CIP for your consideration and discussion. As discussed above and previously, a CIP is required to be submitted to the FAA annually (in October usually) for FAA planning. The attached CIP is similar to, but not the current one on file with the FAA (attached version is also simplified from FAA version for easier reading). With the addition of BIL funds, and other considerations, please use the attached CIP as just a starting point for discussions. This plan will not need to be ironed out at today’s meeting, and no particular action is necessary.

CIP and FAA NPE Plan – DRAFT (Not the current FAA plan)

Note – this plan does NOT include any earmarked FAA Covid relief funds

Black – NPE Annual Earmarks (Assumed NPE Income) AND BIL funds

Red – NPE Project Expenses (NOT including SA or Disc)

Orange - NPE Transfers OUT to other Sponsors

Purple – NPE Transfers or Recips IN from other Sponsors

Green – Non-NPE income - State Apportionment (SA) or Discretionary (Disc)

FY Ending Balance & Notes

Awarded MDT Grants / Loans & Notes

FY Sponsor Match Required & Notes

FISCAL YEAR 		FAA Money 		Notes

90% Total Costs

2

20200

2019 NPE Carryover $151,493 (as reported by FAA 3/26/2019)

2020 NPE $150,000

2020 Project (100%) 	$88,450.84 	Pave Maint – Design (Rwy 12/30, 8/26, twy C, Apron)

Total cost - $88,450.84

$84,650.84 (DOWL contract)

$3,800.00 (Lochner IFE - not included in original grant)

2020 Project (100%) 	$101,165.90 	REIL Replacement – Design / CA / Construction

Total cost - $101,165.90

$35,705.90 (DOWL design / CA contract)

$65,460.00 (Pavlik Bid)

NPE Balance 	$134,257		 (as reported by Scott in phone call - 6/3/21)

2020 GGW Match - $0 			CARES Act pays 100% of 2020 projects

MDT grant $6,000 for REIL – Will not be used

MDT grant $7,500 for Txy Design - Will not be used

MDT grant $5,000 for Pave Maint Design - Will not be used

20212021

2020 NPE Carryover	 $134,257	 (as reported by Scott in phone call - 6/3/21)

2021 NPE 		$150,000

NPE Transfer IN 	$ 50,000	 Transfer IN from CII (recip OUT scheduled 2024) Completed

2022 Project (100%) 	$367,424	 Master Plan / Aerial Survey

Total cost - $367,424

$363,625 (DOWL contract)

$3,799 (Lochner IFE fees / bid ads)

NPE Balance 		$0 		(estimated, as per conversation with Summer 2021)

2021 GGW Match - $0			 CARES Act pays 100% of 2021 projects

(MDT grant applied for fall 2020 – unsuccessful)

2022

2021 NPE Carryover 	$0		 (estimated, as per FAA Summer 2021)

2022 NPE 		$150,000

2022 BIL 		$159,000

2022 Projects SA	 $350,000	 In support of Pave Rehab Project Costs

2022 Project (90%)	 $150,000 	Pavement Maint – Construct (Rwy 12/30, 8/26, twy C, Apron)

Total cost est. $555,000

NPE Balance $159,000 (Assuming NO NPE recip transfer to Big Timber)

2022 GGW Match - $4,600 		MDT grant Jan 2022 / $15,000 for Crack Seal Construct

2023

2022 NPE Carryover 	$159,000	 (Estimated)

2023 NPE	 	$150,000

2023 BIL 		$159,000

2023 Transfer OUT	 $150,000 	“possible”… Recip OUT to Big Timber (expired agreement)

(NOT included in this math, GGW Board decision pending)

(Note – if unable, CII may have some NPEs to cover)

2023 Projects (90%) 	$225,000 	Electrical Upgrades – Design & Construct (Vault & equip)

Total cost est. $250,000

NPE Balance 		$243,000 	(Assuming NO NPE recip transfer to Big Timber)

2023 GGW Match - $25,000 		GGW will apply for MDT grant fall of 2022

2024

2023 NPE Carryover 	$243,000	 (Estimated)

2024 NPE 		$150,000

2024 BIL 		$159,000

NPE Transfer OUT	 $50,000	 Recip OUT to CII (needs agrmnt – for 2021 Transfer)

2024 Projects (90%)	 $135,000	 Twy Relocate - EA (or as per pending preferred MP alternative)

Total cost est. $150,000

NPE Balance		 $367,000

2024 GGW Match - $15,000 		GGW will apply for MDT grant fall of 2023

2025

2024 NPE Carryover	 $367,000	 (Estimated)

2025 NPE		 $150,000

2025 BIL 		$159,000

2025 Projects (90%)	 $150,000	 Twy Relocate / Lighting Upgrades – Design (or as per MP     result)

Total cost est. $167,000

NPE Balance 		$526,000

2025 GGW Match - $17,000 		GGW will apply for MDT grant fall of 2024

2026

2025 NPE Carryover 	$526,000 	(Estimated)

2026 NPE 		$150,000

2026 BIL 		$159,000

2026 Projects Disc 	$2,250,000	 In support of Twy / lighting Project (or as per MP result)

2026 Projects (90%) 	$150,000 	Twy Relocate / Lighting Upgrades - Construction

Total cost est. $2,667,000

NPE Balance		 $685,000

2026 GGW Match - $267,000 		GGW will apply for MDT grant fall of 2025

2027

2026 NPE Carryover	 $685,000	 (Estimated)

2027 NPE 		$150,000

2027 Projects (90%) 	$0 		No scheduled project 2027

NPE Balance 		$835,000

2026 GGW Match - $0 			NO MDT grant app needed fall of 2026

AIRPORT PRIORITIES / GOALS

  - • Current Master Plan / AGIS with special emphasis on o AGIS survey and obstruction data

      - o Twy redesign to correct FAA non-standard issues with heavy emphasis to assure redesign is compatible with all snowplowing issues / needs, etc. Emphasis on alternatives design alternatives (Enviro Assessment / SHPO as needed for projects identified in MP CIP)

  - o SRE Equipment Upgrades (Oshkosh broom with blower)

  - o Terminal Upgrades

  - o Revenue Generation Hangars

  - o Rwy 8/26 xwnd and future eligibility (95% or less vs existing 98%) addressed in the 2013 ALP update)

  - o Ponding Issues / high-water issues around apron & hangar areas

  - o Fuel Farm adjustments

  - o FAA towers to north mitigation

OLD BUSINESS:

OTHER BUSINESS

A motion was made by Kristie Brabeck to adjourn the meeting and seconded. By Darrell Morehouse. Motion carried

Adjourned at 6:50 p.m.

The next meeting is April 12, 2022, at 6:00 PM.

APPROVED BY:					SUBMITTED BY:

_________       ________                     	                      ________________________________

Jayson Nelson, Chairman			           Darcia Schindler, Secretary